## Slide 1: Flexible Benefits System Implementation at Shah Alam Medical Center

## Slide 2: INDEX
The case
Questions for discussion
Key Takeaways

## Slide 3: The Case
Improved responsiveness to employee needs.
Greater coordination of human resource objectives with business strategies.
Added benefits flexibility.
Better cost management.
Shah Alam Medical Center wants to reduce Cost and improve the value and services of its employee benefits coverage.

## Slide 4
A multifunctional team of 13 members from HR, FS, and IS along with 6 technical experts from consulting firm HBS.
A workshop is held for participants to clarify and finalize project objectives and develop a project plan, milestones, and schedule.
The director of FS was chosen as Project Leader and 2 team leaders from HR and IS.
Project completion was set at 10 months.
The Case

## Slide 5: The Case
Members of the Quick team worked on the project on a
part-time basis.
PM given authority over functional managers & project team members for all
project-related decisions
HBS to develop and supply all hardware and software for the new system
Meeting project requirements and time deadlines was imperative

## Slide 6: Questions for Discussion

## Slide 7: What form of project management (basic, program and so on) does this case most closely resemble
Since resources are allotted (borrowed) from the functional units
Since it involves to both the product of the project and the function of the management producing it
Basic Project ManagementMatrix Type
Question-1:

## Slide 8: The Project Manager is also the director of FS, only one of the departments that will be affected by the new benefits system. Does this seem like a good idea? What are the pros and cons of her selection
Does this seem like a good idea?
Yes
Question-2:

## Slide 9: What are the pros and cons of her selection?
Has previously worked on Information Services team.
Good Interpersonal Skills
Better to evaluate the decisions
Act as a center of attention.
Pros:

## Slide 10: Cons:
Overlook the harm it may cause to other stakeholders.
Leverage her position in decision making.
Independent of any one department.

## Slide 11: Question-3 Comment of team members part time assignment and the expectation that they give the project top priority.
• As it the project management approach is Matrix type, it is a very common practice for team members to work part-time on a project.
• Team members will be able to give top priority to the project only when they have their functional managers’ complete support
Comment of team members part time assignment and the expectation that they give the project top priority.
Question-3

## Slide 12: Conflicts:
Conflict over roles & responsibilites
Conflict on Priorities

## Slide 13: Why was an outside firm likely chosen for an important part of the project?
Experts
Shah Alam medical center was in need of technical products.
Time Effective
Training/hiring time.
Cost Effective
Instead of training and hiring new employees, consult an available expertise.
Expanded Customer Base
Customers are main source of revenue for a company.
Long term Collaboration
Collaboration with intel and Microsoft leading to mutual benefit.
Question-4

## Slide 14: What difficulties might this pose to project manager meeting project goals?
Lack of quality check and implementation due to lack of expertise
Profit Sharing
Conflict Of interest
Lack of full control of the manager over product development
PROJECT MANAGER’S PROBLEMS

## Slide 15
Project Manager should have relevant experience in managing new products.
Tasks should be outsourced if the firm does not hold a certain competency
Timeline planning should be done properly - incase a stakeholder defaults, there still should be enough time to complete the project
The project team should have members from all the affected functions
Key Takeaways

## Slide 16: THANK YOU